## Nov-04 (3)
| Adoption of Delivery Agreement | Stakeholder Engagement | Consultation on Preferred Strategy | Plan Placed on Deposit | Advertise Alternative Sites | Examination | Publication of Binding Inspector's Report | LDP Adopted
Blaenau Gwent
Brecon Beacons NP
Bridgend
Caerphilly | 2006-05-01 | Jul 06-Sep 06 | Jul 07-Aug 07 | Sep 08-Oct 08 | Jan 09-Feb 09 | 2010-03-01 | 2010-12-01 | 2011-02-01
Cardiff | Apr 06-May 06 | Jan 06-Jul 06 | Mar 07-Ap 07 | Jan 08-Feb 08 | May 08-Jun 08 | Sep 08-Oct 08 | Sep 09-Oct 09 | 2009-12-01
Carmarthenshire
Ceredigion
Conwy | 2005-09-01 | Oct 05-Jan 06 | Apr-May 06 | 2007-04-01 | 2007-08-01 | Apr-Jun 08 | 2008-12-01 | 2009-02-01
Denbighshire | 2005-11-01 | Apr-Nov 05 | Apr-06-Jul 07 | Oct 07-Feb08 | Mar-Sept 08 | Jan-Mar-09 | Apr-Oct 09 | Oct-Nov 09
Flilntshire
Gwynedd
Isle of Anglesey
Merthyr Tydfil | 2006-01-01 | Oct 05-Aug 06 | Jan-Feb 07 | Oct-Nov 07 | Feb-Apr 08 | Oct-Dec 08 | Jul-Sep 09 | Oct-Nov 09
Monmouthshire
Neath Port Talbot
Newport
Pembrokeshire & NP
Powys
Rhondda Cynon Taff | 2005-12-01 | Sept 05-Jun 06 | Jul-Aug 06 | Jun-July 07 | Sept-Oct 07 | Aug-Oct 2008 | 2009-02-01 | 2009-03-01
Snowdonia
Swansea
Torfaen | 2005-12-01 | Dec 05-May 06 | Oct-Nov 06 | Nov-Dec 07 | Feb-Mar 08 | Nov 08-Jan 09 | Aug-Oct 09 | 2009-12-01
Vale of Glamorgan
Wrexham

## Nov-04 (2)
| 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11
| Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec
Blaenau Gwent
Brecon Beacons NP
Bridgend
Caerphilly |  |  | DA | SE |  |  |  | PSt |  |  |  |  | Dep | Aas |  |  |  | Ex |  |  | Ir | Ado
Cardiff |  |  | DA | SE |  |  | PSt |  |  | Dep | Aas |  | Ex |  |  | Ir | Ado
Carmarthenshire
Ceredigion
Conwy | DA | SE | PSt |  |  |  | Dep | Aas |  |  | Ex |  | Ir | Ado
Denbighshire | DA | SE | [5 empty] | PSt |  | Dep |  | Aas |  | Ex |  | Ir | Ado
Flilntshire
Gwynedd
Isle of Anglesey
Merthyr Tydfil |  | DA |  | SE |  | PSt |  |  | Dep | Aas |  |  | Ex |  |  | Ir | Ado
Monmouthshire
Neath Port Talbot
Newport
Pembrokeshire & NP
Powys
Rhondda Cynon Taff | DA |  | SE | PSt |  |  |  | Dep | Aas |  |  |  | Ex |  |  | Ir | Ado
Snowdonia
Swansea
Torfaen | DA |  | SE |  | PSt |  |  |  | Dep | Aas |  |  | Ex |  |  | Ir | Ado
Vale of Glamorgan
Wrexham

## Nov-04
| Adoption date of the existing local plan | Issues report published | Draft Plan published | Placed on Deposit | Pre-Inquiry / Proposed Changes | Public Inquiry begins | Inspector's Report | Mods | UDP adopted
Blaenau Gwent | Blaenau Gwent LP June 96 |  | 1999-03-01 | 2000-07-01 |  | 2002-10-01 | 2003-05-01 | Apr-04 Dec-04
Brecon Beacons NP | Brecon Beacons LP May 99 | Spr 2000 | 2002-05-01 | 2004-06-01
Bridgend | Ogwr Borough LP Apr 95 | 1998-01-01 | 2000-07-01 | 2001-05-01 |  | 2002-04-01 | 2003-05-01 | 2004-02-01 | 2005-01-01
Caerphilly | Islwyn LP Jan 96 |  | 1998-08-01 | 1999-09-01 |  | 2001-01-01 | 2002-05-01 | 2003-02-01 | LDP
Rhymney Valley District LP Nov 96 (Approved for DC purposes)
Cardiff | Cardiff City LP Jul 96 | 1997-07-01 | Sum 01 | 2003-10-01 | LDP ?
Carmarthenshire | Dinefwr LP Apr 98 | 1998-12-01 | 2000-12-01 | 2002-12-01 | 2003-11-01 | 2004-03-01
Carmarthen LP Aug 99
Ceredigion | No coverage |  | Spr 01 | 2002-10-01 | 2004-03-01 | 2005-01-01
Conwy | Llandudno LP (1994) |  | 2001-04-01 | 2004-04-01 | LDP
Colwyn Borough LP (1999)
Denbighshire | Glyndwr LP 94 |  | 1996-11-01 | 1999-05-01 |  | 2000-10-01 |  |  | 2002-08-01
Rhuddlan LP
Flilntshire | Delyn LP (1993) North Flintshire LP96 |  | 2000-05-01 | 2003-10-01 | 2004-06-01
Alyn and Deeside LP Approved for DC purposes
Gwynedd | Patchy |  | 2002-07-01 | 2004-06-01 |  | 2005-04-01
Isle of Anglesey |  |  | 2000-05-01 | 2001-11-01 | Nov-02 | 2003-06-01 | 2004-07-01
Merthyr Tydfil | Merthyr Tydfil LP May 99 | 2000-08-01 |  | LDP
Monmouthshire | Monmouthshire Borough LP May 97 |  | 1999-02-01 | 2001-10-01 | 2003-12-01 | 2004-09-01
Neath Port Talbot | Neath Borough Local Plan | Spr 2000 | 2000-07-01 | 2003-07-01 | 2004-03-01
Newport |  | 1997-03-01 | 1998-07-01 | 1999-11-01 | 2003-04-01 | 2004-11-01
Pembrokeshire & NP | North Pembrokeshire LP 96 | 2000-03-01 |  | 2002-05-01 | 2003-07-01 | 2004-01-01
Powys | Radnorshire LP Apr 99 | Sum 2000 | 2003-02-01 | 2004-06-01
Brecknock LP Oct 97
Rhondda Cynon Taff | Rhondda LP Feb 98 |  | LDP
Snowdonia |  |  |  | 2003-10-01 | Sum-04 | Aut-04
Swansea | Swansea LP Jan 99 |  | 2003-02-01 | 2005-07-01
Torfaen |  | 2000-06-01 |  | LDP
Vale of Glamorgan | Area local plans | 1997-09-01 | 1997-09-01 | 1998-04-01 |  | 1999-06-01 | 2000-11-01 | Spr -03 Jun-04
Wrexham | Wrexham Mylor 96 |  | 1998-11-01 | 2000-06-01 |  | 2002-06-01 | 2003-02-01 | 2003-08-01