## Action log
Area/Project: |  | Meeting Action Log - 2nd July 2015 | Colour | Status | Count
|  |  | RED | Due | 8
|  |  | AMBER | Open | 0
Distribution |  | All members of the Homebuilders Health and Safety Forum | GREEN | Done | 6
|  |  | Date: | 31st August 2015
Ref | Issue | Action | Resp. | Due | Status | Comment
1 | Dust in Construction | Strategy, Information pack and guidance to be issued for implementation by members | DH/EW | 2015-08-30 | DUE | Presentation pack required for employees to compliment guidance already issued
2 | London Best Practice Guide Dust and Emissions | Guide to be issued to members | VC | 2015-05-30 | Done | Issued on 2nd June 2015
3 | Review extraction equipment with Hire Association Europe | Hold meeting with HAE, to establish what extraction equipment is available and limitations/advantages. | DH/EW | 2015-08-31 | DUE | Further review with HAE required and additional detail provided on available extraction equipment - Consider if membership of HAE will provide benefits to the forum
4 | Guide to a Scaffold Specification | Final document to be issued following amendment | VC | 2015-08-31 | DUE | Final review required with HSE and scaffold designers and document to be issued
5 | Review Passive Fall Protection with HSE | Meeting to be held with HSE on use of passive fall protection measures such as soft landing systems | EW/SA | 2015-07-02 | DUE | HSE to provide further feedback following a review with suppliers. Zip ties now allowed.
6 | Injury Stats 2014/15 | All members to review accuracy of data and collection methods - Data to be issued on time | All/MP/DM | 2015-08-31 | Done | Data for 2014/15 to be reviewed by all for accuracy and annual report to be provided for the July meeting
7 | Health and Safety Charter | Charter to be reviewed, including company logo's and issued | All | 2015-05-30 | Done | Charter updated and approved. VC to issue to all members - Issued 1st June 2015
8 | Charter Action Plan | Action Plan to be reviewed and updated and actions projected through to 2016 | VC | 2015-08-31 | DUE | Plan updated but further consideration given to 2016 objectives (consider with meeting action log)
9 | Safe Installation of Roof Trusses | Consideration given to methods of safe installation of roof trusses | CD | 2015-08-31 | DUE | Feedback on current installation methods to be provided to CD. Presentation on findings to be provided at the next meeting
10 | CDM | Review impact CDM 2015 will have on the homebuilding Industry | SA | 2015-03-30 | DUE | Further review of impact of CDM to be undertaken by the sub-group in June. On review it appears that the members have developed their own in-house systems and the NHBC/HBF seminars have provided further focus. It was agreed to postpone the sub-group meeting pending further discussion at the July forum meeting. Briefing note for members required
11 | Consortium Agreement | Agreement to be updated to reflect changes in CDM | VC | 2015-05-07 | Done | Agreement updated and issued to members in April 2015. If members have not received a copy they can contact VC or DM for a further version
12 | Slips/Trips Posters | Examples of appropriate Slips/Trips posters to be provided which could be used for HBF campaign | MP | 2015-08-31 | Done | MP agreed to coordinate the provision of revised posters/campaign on behalf of the group now completed
13 | Multi-Storey Structures | Members requested to provide support for project via CONIAC on health and safety in multi-storey structures | ALL/BO | 2015-05-30 | Done | Members to provide nominations to support the project to Barry Oliver
14 | Impact wrenches for scaffold fittings | Review current guidance on the use of impact wrenches for tightening scaffold fittings | VC/HSE | 2015-08-31 | DUE | HSE to review if there is any specific guidance that they can provide. NASC to be contacted by VC to establish what their current guidelines are
15 | Timber Frame Structures | Feedback to be provided following discussions at the Forum on the HSE letter to the Structural Timber Association on controls for construction of timber frame units less than 600m2 | DM | 2015-06-30 | Done
END - insert new lines above here
Task- force
Note on G7: Number done that were due in the last 7 days
Homebuilders Health and Safety Forum Action Log